## Sheet1
A web-based dashboard for updating the market value of football players
Sude Fidan 21068639, William Barnes 21031340, Fiorella Scarpino 21010043, Jack Douet 21025153,Troy Akbulut 21015976
Project Start Date: | 2023-02-02 | Project Finish Date: |  |  | 2023-04-25
Enter Company Name in cell B2.
TASK | ASSIGNED TO | PROGRESS | START | END | WEEK1 | WEEK2 |  | WEEK3 |  | WEEK4 |  | WEEK5 |  | WEEK6 |  | WEEK7 |  | WEEK8 |  | WEEK9 |  | WEEK10 |  | WEEK11
[5 empty] | 2023-02-02 | 2023-02-06 | 2023-02-09 | 2023-02-13 | 2023-02-16 | 2023-02-20 | 2023-02-23 | 2023-02-27 | 2023-03-02 | 2023-03-06 | 2023-03-09 | 2023-03-13 | 2023-03-16 | 2023-03-20 | 2023-03-23 | 2023-03-27 | 2023-03-30 | 2023-04-17 | 2023-04-20 | 2023-04-24
Planning
Task1: Team and project choice | All | 100% | 2023-02-02 | 2023-02-06
Task 2: Introduction | All | 0%
Task 2: Project Aim | William Barnes | 100% | 2023-02-06 | 2023-02-06
Task 3: Smart Objectives | Sude Fidan + Fiorella Scarpino+Jack Douet | 100% | 2023-02-06 | 2023-02-09
Task 4: Literature Review | Jack Douet | 50% | 2023-02-20
Task 5: Requirements | Troy Akbulut + Jack Douet | 100% | 2023-02-09 | 2023-02-16
Task 6: Sustainability | Fiorella Scarpino | 100% | 2023-02-20 | 2023-02-23
Design
Task 1: Wire frames | William Barnes | 100% | 2023-02-16 | 2023-02-17
Task 2: Database design | Troy Akbulut | 100% | 2023-02-16 | 2023-02-20
Task 3: Use case diagram | Sude Fidan | 100% | 2023-02-20 | 2023-02-20
Task 4: Class diagram | Sude Fidan + Fiorella Scarpino | 100% | 2023-02-16 | 2023-02-16
Task 5: Sequence diagram | Troy Akbulut | 100% | 2023-02-20 | 2023-02-20
Task 6: Test Cases | Sude Fidan | 0%
Task 7: Decomposition diagram | Troy Akbulut | 100% | 2023-02-16 | 2023-02-16
Development
Task 1: Static pages | William Barnes | 50% | 2023-02-20
Task 2: Dynamic Jinja elements | Jack Douet+William Barnes | 20% | 2023-02-20
Task 3: Flask routes | Jack Douet | 20% | 2023-02-20
Task 4: Dynamic Javascript elements | Fiorella Scarpino | 0%
Task 5: Transfer value algorithms | Sude Fidan | 100% | 2023-02-23 | 2023-02-23
Task 6: Prediction algorithms | Troy Akbulut | 100% | 2023-02-23 | 2023-02-23
Validation
Task 1: Testing input validation | William Barnes | 0%
Task 1: Testing prediction algorithms | Sude Fidan | 0%
Task 2: Testing transfer algorithms | Troy Akbulut | 0%
Task 3: Testing static pages | Jack Douet | 0%
Task 5: Testing viewpoints | Fiorella Scarpino | 0%
Phase 5 Title
Task 1
Task 2
Task 3
Task 4
Task 5